## Sheet1
Task ID | Task Name | Assigned | Task Status | Exepected Time To Finish | Actual Time To Finish
01-MCAL | PWM Module | Bassel Yasser | 100 | FINISHED
02-HAL | HPWM | Bassel Yasser | 100 | FINISHED
03-Documentation | Driver Docs | Bassel Yasser | 95 | 2023-12-04 | 2023-12-04
4 | Design external interrupts | Sharpel Malak | 100 | 1 hour | 3 hours
5 | Design PWM with normal mode | Sharpel Malak | 100 | 4 hours | 6 hours
6 | Implement external interrupts | Sharpel Malak | 100 | 2 hours | 2 hours
7 | Implement PWM with normal mode | Sharpel Malak | 100 | 2 hours | 3 hours
8 | test external interrupts Driver | Sharpel Malak | 100 | 1 hour | 1 hour
9 | test PWM with normal mode Driver | Sharpel Malak | 100 | 1 hour | 2 hours