## Sheet1
Task ID | Task Name | Assigned | Task Status | Exepected Time To Finish | Actual Time To Finish
1 | MCAL _PWM Module Design | Bassel Yasser | 100 | 1 hour | 1.5 hour
2 | HAL_HPWM Design | Bassel Yasser | 100 | 1 hour | 30 minutes
3 | Driver Docs | Bassel Yasser | 100 | 1 hour | 1.25 hour
4 | MCAL_PWM Module Implementation | Bassel Yasser | 100 | 1 hour | 1 hour
5 | HAL_HPWM Implementaton | Bassel Yasser | 100 | 45 minutes | 45 minutes
6 | PWM Module Testing | Bassel Yasser | 100 | 30 minutes | 30 minutes
7 | Design external interrupts | Sharpel Malak | 100 | 1 hour | 3 hours
8 | Design PWM with normal mode | Sharpel Malak | 100 | 4 hours | 6 hours
9 | Implement external interrupts | Sharpel Malak | 100 | 2 hours | 2 hours
10 | Implement PWM with normal mode | Sharpel Malak | 100 | 2 hours | 3 hours
11 | test external interrupts Driver | Sharpel Malak | 100 | 1 hour | 1 hour
12 | test PWM with normal mode Driver | Sharpel Malak | 100 | 1 hour | 2 hours
13 | HAL_PushButton Design | Sherif Ashraf | 100 | 45 minutes | 45 minutes
14 | HAL_PushButton Implementation | Sherif Ashraf | 100 | 30 minutes | 1 hour
15 | HAL_PushButton Testing | Sherif Ashraf | 100 | 20 minutes | 15 minutes
16 | HAL_LED Design | Sherif Ashraf | 100 | 30 minutes | 30 minutes
17 | HAL_LED Implementation | Sherif Ashraf | 100 | 30 minutes | 45 minutes
18 | HAL_LED Testing | Sherif Ashraf | 100 | 20 minutes | 15 minutes
19 | MCAL_DIO Design | Sherif Ashraf | 100 | 1 hour | 1 hour
20 | MCAL_DIO Implementation | Sherif Ashraf | 100 | 1.5 hour | 2 hours
21 | MCAL_DIO Testing | Sherif Ashraf | 100 | 30 minutes | 45 minutes
22 | COMMON_STDTYPES | Sherif Ashraf | 100 | 10 minutes | 10 minutes
23 | COMMON_BitMath | Sherif Ashraf | 100 | 10 minutes | 10 minutes
24 | MCAL_TIMER0 Design | Alaa Hisham | 100 | 45 minutes | 45 minutes
25 | MCAL_TIMER0 Implementation | Alaa Hisham | 100 | 1 hour | 1 hour
26 | MCAL_TIMER0 Testing | Alaa Hisham | 100 | 30 minutes | 15 minutes
27 | HAL_TIMER0_HANDLER Design | Alaa Hisham | 100 | 30 minutes | 30 minutes
28 | HAL_TIMER0_HANDLER Implementation | Alaa Hisham | 100 | 1 hour | 1 hour
29 | HAL_TIMER0_HANDLER Testing | Alaa Hisham | 100 | 30 minutes | 1 hour
30 | HAL_MOTOR Design | Alaa Hisham | 100 | 15 minutes | 15 minutes
31 | HAL_MOTOR Implementation | Alaa Hisham | 100 | 30 minutes | 30 minutes
32 | HAL_MOTOR Testing | Alaa Hisham | 100 | 30 minutes | 15 minutes
33 | COMMON_VECTOR Table | Alaa Hisham | 100 | 15 minutes | 15 minutes
34 | Integrate all Drivers | Team | 100 | 6 hours | 8 hours
35 | APP | Team | 100 | 3 hours | 5 hours
36 | Documentation | Team | 100 | 4 hours | 6 hours